## Sundial Open Issue Mac_Windows
Windows
Sl | Issue id | Summary | Reporter | Priority | Status
1 | RA-832 | [profile settings] The old organization name is displayed in the profile settings instead of the updated organization name. | pushpa | Medium | Sprint backlog
2 | RA-781 | [Organization] 1. Organization name is not displaying proper when organization created with maximum characters. 2. Tool tip is not coming for the organization which is having maximum characters. | pushpa | Medium | Test Ready
3 | RA-846 | Activity capturing stops in System 1 when the user logs into System 2 with the same credentials | pushpa | Medium | Sprint backlog
4 | RA-842 | [Onboarding screens] Toggle button is not disable in the general settings when user disable the 'Idle Time Detection and 'Launch Sundial on system startup' | pushpa | High | Test Ready
5 | RA-798 | [Windows 11] Lock app & Idle time not displaying properly. | pushpa | Medium | In development
6 | RA-870 | [Windows] [Schedule] The Save button is getting enabled when the user switches to other languages or logs into the application with the same account. | pushpa | Low | Test Ready
7 | RA-860 | The system became slow and unresponsive when restarting after installing the Sundial package | pushpa | Highest | Analysis
Mac
8 | RA-863 | [Schedule] The highlighted start and end date fields are not being removed. | pushpa | Low | Test ready
9 | RA-864 | [MAC] [General settings] The idle time detection toggle button is getting enabled even when the user disables it. | pushpa | High | Test ready
10 | RA-865 | [MAC] Ui issues in sign in page after switching to the other languages. | pushpa | Medium | Test ready
11 | RA-866 | [MAC] An organization list window popup is displayed when the user clicks on the organization list dropdown. | pushpa | Low | Test ready
12 | RA-867 | [Mac] Activities are not being captured properly when the user login to the application and stays on the Sundial page. | pushpa | High | Sprint backlog
13 | RA-869 | [Mac] [Schedule] The Save button is getting enabled when the user switches to other languages or logs into the application with the same account. | pushpa | Low | Sprint backlog

## Ralvie_Open_Issues
Ralvie Cloud
1 | RC-1363 | [Timesheet] Timesheet events are not being tagged properly. | Payel Chowdhury | Test ready | High
2 | RC-1476 | [Timesheet] Project auto tagging is not working | Payel Chowdhury | Test ready | Medium
3 | RC-1492 | [Login] The application is unable to maintain a user login session for the expected duration of 24 hours. | Payel Chowdhury | Testing | High
4 | RC-1496 | [Timesheet] When logging an event and then filtering by "Unlogged," the event does not get removed from the screen. Additionally, the event can be logged multiple times, but the time duration appears as 00h 00m 00s. | Payel Chowdhury | Backlog | High
5 | RC-1526 | [Timesheet > Project auto select] For certain events, the project is not being auto-tagged in the "Timesheet > Project" field but is correctly appearing in the "Title" field. | Payel Chowdhury | Test ready | High
6 | RC-1553 | [Organization] Enhancement request : When a user switches to a different organization within the application, a notification should be displayed to confirm the switch | Payel Chowdhury | Code review | Medium
7 | RC-1568 | [Timesheet > Project auto select] Based on trained data , auto selecting is not happening | Payel Chowdhury | Backlog | High
8 | RC-1570 | [Timesheet > Project auto tagging] Enhancement Request: Display message for Untrained data | Payel Chowdhury | Analysis | Medium
9 | RC-1571 | [Timesheet > Project auto tagging] Enhancement Request: AI-Based project auto-tagging for similar data | Payel Chowdhury | Test ready | High
10 | RC-1402 | [Control panel] Next step button should be disabled untill the user enters the data into fields. | Kirana | Analysis | Medium
11 | RC-1521 | UI Glitch: Unexpected Module Panel Minimization on User Interaction | SRINIVAS RAO | Code review | Low
12 | RC-1522 | [UI/Functionality][SUNDIAL] Info details dialog is not closing if user clicks outside the dialog | PARV PATHAK | Backlog | Medium
13 | RC-1559 | [Subscription] Unable to unarchive the member and projects once the subscription ends. | Kirana | Analysis | Medium
14 | RC-1564 | UI ¦ Toggle Button on Sundial Schedule Page is Not Functioning Smoothly | SRINIVAS RAO | Backlog | Medium
15 | RC-1572 | [Timesheet] The searched record is not appearing | pushpa | Backlog | lowest
16 | RC-1577 | [Sundial][User experience] In sundial, events of both yesterday and today are displaying under today section under activities | PARV PATHAK | Backlog | Medium
17 | RC-1588 | [Members]As an Admin or Owner, both can reassign from the project but can still view it in their login, vice versa. | Kirana | Backlog | Medium